## administration
Name | Task types | Status | Instructions:
CHAI JUAN YANG | REQ1 (UML diagram Design rationale) | DONE | Please rename the file and copy the shared link to your repository. We won't give any students an Editor access, so please make a separate copy =). Due to academic integrity, failure to do so may result in 0 mark.
LIANG DI ZHEN | REQ2 (UML diagram Design rationale) | DONE | Put your team members' name in "Name" column (A2-A5)
HENG ZI YING | REQ3 (UML diagram Design rationale) | DONE | Please go to another tab below (Assignment 1, 2 or 3)
TOGETHER | REQ4 (UML diagram Design rationale) |  | As a team, discuss and list on what tasks that need to be done along with its type.
| REQ5 (UML diagram Design rationale) |  | Ideally you'll assign yourself to a task. However, you're welcome to assign a task to someone if everyone agrees on that.
While working on a task, please change the status from "TODO" to "IN PROGRESS" to inform your team that you are working on that task.
| Discussion (Physical) |  | Once you're done, log the date you've completed the task. Feel free to add extra notes if that help your team understands what've you done with the task. Ideally you'll write a brief reflection on the completed task.
| Discussion (Online) |  | Ideally a task need to be atomic (only one thing), so it shouldn't be shared/done by two people except as a whole "Team discussion".
| REQ 1 Coding |  | In a case that you're unable to complete the task and it will be taking over by someone else, set the status to INCOMPLETE, and create a fresh new log with new planning date and contributor's name.
| REQ 2 Coding |  | Feel free to add more contribution types if you think they are insufficient
| REQ 3 Coding |  | Your markers may have a look at the Version History to make decisions if there are imbalance of contributions. So, please notify your lab demonstrators if that's the case.
REQ 4 Coding
Req 5 Coding
Interaction Diagram
UML diagram and Design Rationale

## Assignment 1
Task/Contribution(~30 words) | Contribution type | Planning Date | Contributor | Status | Actual Completion Date | Extra notes
First meeeting discussion | Discussion (Online) | 2023-03-28 | TOGETHER | DONE | 2023-03-28 | We had a 2 hours meeting to read the assignment specifications together and distributed work equally among team members. The team agreed with the jobs allocated.
List out all actors, items, and grounds in the whole assignment | Discussion (Online) | 2023-03-28 | TOGETHER | DONE | 2023-03-28
Second Meeting discussion | Discussion (Physical) | 2023-04-02 | TOGETHER | DONE | 2023-04-02 | We organised a 5 hours meeting on campus to discuss each of the tasks according to the requirements
Design the class structure of items in the game | REQ1 (UML diagram Design rationale) | 2023-04-02 | CHAI JUAN YANG | DONE | 2023-04-02 | Task 1 Completed
Design the class structure of items in the game | REQ2 (UML diagram Design rationale) | 2023-04-02 | LIANG DI ZHEN | DONE | 2023-04-02 | Task 2 Completed
Design the class structure of items in the game | REQ3 (UML diagram Design rationale) | 2023-04-02 | HENG ZI YING | DONE | 2023-04-02 | Task 3 Completed
Third Meeting Discussion | Discussion (Physical) | 2023-04-04 | TOGETHER | DONE | 2023-04-04 | Review the 3 completed tasks so far, discuss about the remaining tasks allocation.
Design the class structure of items in the game | REQ4 (UML diagram Design rationale) | 2023-04-04 | TOGETHER | DONE | 2023-04-10 | Task 4 completed on the final meeting
Design the class structure of items in the game | REQ5 (UML diagram Design rationale) | 2023-04-04 | TOGETHER | DONE | 2023-04-10 | Task 5 completed on the final meeting
Last Meeting Discussion | Discussion (Physical) | 2023-04-10 | TOGETHER | DONE | 2023-04-10 | Review all the tasks and to finalize all diagrams and design rationale.

## Assignment 2
Task/Contribution(~30 words) | Contribution type | Planning Date | Contributor | Status | Actual Completion Date | Extra notes
First Meeting for Assignment 2 | Discussion (Online) | 2023-04-19 | TOGETHER | DONE | 2023-04-19 | Meeting ended.
Codes for Requirement 1 | REQ 1 Coding | 2023-04-20 | CHAI JUAN YANG | DONE | 2023-04-20 | Codes Completed and pushed to REQ 1 branch.
Second Meeting for Assignment 2 | Discussion (Online) | 2023-04-20 | TOGETHER | DONE | 2023-04-20 | Meeting ended.
Coding Session for Requirement 2 | REQ 2 Coding | 2023-04-21 | LIANG DI ZHEN | DONE | 2023-04-22 | Codes Completed and pushed to REQ 2 branch.
Coding Session for Requirement 3 | REQ 3 Coding | 2023-04-22 | HENG ZI YING | DONE | 2023-04-26 | Codes Completed and pushed to REQ 3 branch.
Coding Session for Requirement 4 | REQ 4 Coding | 2023-04-25 | TOGETHER | DONE | 2023-05-02 | Codes Completed and pushed to REQ 4 branch.
Coding Session for Requirement 5 | Req 5 Coding | 2023-04-26 | TOGETHER | DONE | 2023-05-02 | Codes Completed and pushed to REQ 5 branch.
Discussion and debug session (3rd meeting) | Discussion (Physical) | 2023-04-29 | TOGETHER | DONE | 2023-04-29 | Meeting on campus ended.
To discuss and debug possible bugs (4th meeting) | Discussion (Physical) | 2023-04-30 | TOGETHER | DONE | 2023-04-30 | Meeting on campus ended.
Sequence Diagram and UML updates | Interaction Diagram | 2023-05-05 | TOGETHER | DONE | 2023-05-06 | Completion of Sequence Diagram and Uml , design rationale updates

## Assignment 3
Task/Contribution(~30 words) | Contribution type | Planning Date | Contributor | Status | Actual Completion Date | Extra notes
First physical meeting to discuss about task allocation | Discussion (Physical) | 2023-05-05 | TOGETHER | DONE | 2023-05-05
Task 1 | REQ 1 Coding | 06/052023 | CHAI JUAN YANG | DONE | 2023-05-10 | Joined consultation to ask about GoldenFogDoors
Task 2 | REQ 2 Coding | 2023-05-06 | TOGETHER | DONE | 2023-05-07 | Task 2 was completed as a group
In class consultation and discussion | Discussion (Physical) | 2023-05-10 | TOGETHER | DONE | 2023-05-10
Task 3 | REQ 3 Coding | 2023-05-11 | LIANG DI ZHEN | DONE | 2023-05-13 | Completed on time
Task 4 | REQ 4 Coding | 2023-05-13 | HENG ZI YING | DONE | 2023-05-15 | Completed on time
Discussion for creative requirement | Discussion (Online) | 2023-05-15 | TOGETHER | DONE | 2023-05-15 | Creative requirement decided and updated
Task 5 | Req 5 Coding | 2023-05-15 | TOGETHER | DONE | 2023-05-18
UML and Design Rationale | UML diagram and Design Rationale | 2023-05-18 | TOGETHER | DONE | 2023-05-20
Short discussion to finalise codes and design rationale | Discussion (Online) | 2023-05-20 | TOGETHER | DONE | 2023-05-20